## Sheet1
Dự án | Website bán Thiết bị điện tử
Công nghệ | Reactjs + Wordpress + MySql
Thành viên | 3119410021 - Bùi Tấn Âu 3119410491 - Nguyễn Phùng Vinh 3119410035 - Nguyễn Ngọc Báu 3119410055 - Phan Hữu Cường
|  |  |  | September | [20 empty] | October | [30 empty] | November
|  |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12
Task name | Owner | Start date | End date | 2022-09-10 | 2022-09-11 | 2022-09-12 | 2022-09-13 | 2022-09-14 | 2022-09-15 | 2022-09-16 | 2022-09-17 | 2022-09-18 | 2022-09-19 | 2022-09-20 | 2022-09-21 | 2022-09-22 | 2022-09-23 | 2022-09-24 | 2022-09-25 | 2022-09-26 | 2022-09-27 | 2022-09-28 | 2022-09-29 | 2022-09-30 | 2022-10-01 | 2022-10-02 | 2022-10-03 | 2022-10-04 | 2022-10-05 | 2022-10-06 | 2022-10-07 | 2022-10-08 | 2022-10-09 | 2022-10-10 | 2022-10-11 | 2022-10-12 | 2022-10-13 | 2022-10-14 | 2022-10-15 | 2022-10-16 | 2022-10-17 | 2022-10-18 | 2022-10-19 | 2022-10-20 | 2022-10-21 | 2022-10-22 | 2022-10-23 | 2022-10-24 | 2022-10-25 | 2022-10-26 | 2022-10-27 | 2022-10-28 | 2022-10-29 | 2022-10-30 | 2022-10-31 | 2022-11-01 | 2022-11-02 | 2022-11-03 | 2022-11-04 | 2022-11-05 | 2022-11-06 | 2022-11-07 | 2022-11-08 | 2022-11-09 | 2022-11-10 | 2022-11-11 | 2022-11-12 | 2022-11-13 | 2022-11-14 | 2022-11-15 | 2022-11-16 | 2022-11-17 | 2022-11-18 | 2022-11-19 | 2022-11-20 | 2022-11-21 | 2022-11-22 | 2022-11-23 | 2022-11-24 | 2022-11-25 | 2022-11-26 | 2022-11-27 | 2022-11-28 | 2022-11-29 | 2022-11-30 | 2022-12-01 | 2022-12-02 | 2022-12-03 | 2022-12-04 | 2022-12-05 | 2022-12-06 | 2022-12-07 | 2022-12-08 | 2022-12-09 | 2022-12-10 | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-14 | 2022-12-15 | 2022-12-16 | 2022-12-17 | 2022-12-18 | 2022-12-19 | 2022-12-20
Project Definition
Tìm hiểu về Open source | Âu, Báu, Cường,Vinh | 2022-09-10 | 2022-09-23
Thảo luận và chọn đề tài để phát triển
Thảo luận về công nghệ được sử dụng để làm đề tài
Chốt công nghệ
Set up
Set up môi trường để chạy Reactjs + Wordpress + Xampp |  | 2022-09-25 | 2022-09-30
Design UI
Design in figma | Âu, Báu, Cường,Vinh | 2022-09-24 | 2022-10-01
Design API
API for authenticate | Báu ,Cường | 2022-10-02 | 2022-10-05
API list product in cart
API product detail
API product list
API category
API List of orders purchased by account
API status of order
API search
API for profile
API for checkout
FE - Coding Reactjs
UI for Sign-up, Sign-in, | Vinh | 2022-10-06 | 2022-10-10
UI header,footer |  | 2022-10-11 | 2022-10-14
UI side bar |  | 2022-10-15 | 2022-10-19
UI navigation |  | 2022-10-20 | 2022-10-25
UI product item |  | 2022-10-26 | 2022-10-30
UI cart |  | 2022-10-31 | 2022-11-03
UI product detail | Âu | 2022-11-04 | 2022-11-07
UI filter |  | 2022-10-06 | 2022-10-12
UI slider |  | 2022-10-13 | 2022-10-14
UI my account |  | 2022-10-15 | 2022-10-21
UI detail order |  | 2022-10-22 | 2022-10-29
UI my order | Cường | 2022-10-18 | 2022-10-21
Coding Backend with Wordpress
API for authenticate | Cường | 2022-10-06 | 2022-10-09
API list product in cart |  | 2022-10-10 | 2022-10-11
API product detail |  | 2022-10-12 | 2022-10-13
API product list |  | 2022-10-14 | 2022-10-15
API category |  | 2022-10-16 | 2022-10-17
API List of orders purchased by account | Báu | 2022-10-06 | 2022-10-13
API status of order |  | 2022-10-14 | 2022-10-21
API filter |  | 2022-10-22 | 2022-10-27
API for user |  | 2022-10-28 | 2022-11-02
API for checkout |  | 2022-11-03 | 2022-11-06
Testing
Testing |  | 2022-11-08 | 2022-11-10